## Sheet1
Project management
task name | description | start date | end date | duration | % done
investigate | understand all functions - register/ bit/ fields: 20% - counter: 20% - counting mode: 20 % - APB: 30% - Interrupt: 10% | 2024-12-11 | 2024-12-14 | 3 | 100
design specification | Design specification making - feature list: 10% - block diagram: 10% - IO port list: 10% - waveform: 30% - logic diagram: 40% | 2024-12-11 | 2024-12-18 | 7 | 100
RTL coding | calculate % based on your block diagram for example: your module has 5 blocks -> each block can be 20% Note that % of each blocks can be different based on your estimation | 2024-12-12 | 2024-12-19 | 7 | 100
compilation | compile DUT only: 50% write simple TB, instantate DUT and run 1 simulation (no stimulus) without Warnings/Errors: 50% | 2024-12-20 | 2024-12-22 | 2 | 100
verification plan |  | 2024-12-23 | 2024-12-30 | 7 | 100
build env | build necessary components for your env: APB master, checker, scripts, report, … | 2024-12-23 | 2024-12-25 | 2 | 100
1 pass | 1 pass scenario - sanity test: a testcase that cover some basic functions of the design 1. write 0xFFFF to TDR0 and read back 2. enable interrupt 3. start timer 4. check if interrupt can be asserted when timer reaches TDR0 value | 2024-12-26 | 2024-12-29 | 3 | 100
all pass | % done is calculated based on your items that was passed in your verification plan | 2024-12-26 | 2025-01-02 | 7 | 100
coverage | toggle: 20% statement: 20% expression: 20% condition: 20% branch: 20% | 2025-01-03 | 2025-01-05 | 3 | 100
total |  |  |  | 30 | 100